## Iterable Sheet
Pointers | Prompt(input) | Prompt(output)
Short Description | Ingest sharepoint ppd data in S3 Raw zone
Long Description
1.Provide a detailed description of the change (change description should focus on component functionality not the project or solution): | to ingest ppd metadata and pdfs from PPD Share point into EDB S3 Raw Bucket
2.Impact Analysis (Provide an impact analysis summary including, where applicable, any description of change in functionality, business processes, and impact on other systems.) | data ingestion
Propose Tab
1.Describe the business and technical drivers for implementing the change | to bring PPD data available on PPD Sharepoint into EDB S3 Raw Bucket,<placeholder ITSME>,"comments"
a.Is this a new custom component (Yes/No): | Yes
Development Plan
1.Is new code/configuration being developed or is current code being update? | Yes,comments
updated,comments
2.Source code reviews will be executed and the executed source code review information will be documented in the Development Execution Notes. | Yes,<placeholder>
3.List any validation artifacts to be created/modified.
a.Are Requirements being created/updated (Yes/No)? | Yes, www.jira.com
b.Is a Component Design Artifact being created/updated (Yes/No)? | Yes
c.Is an EDB Application Security Plan Custom Component Attachment being created /updated (Yes/No)? | Yes
d.Is the EDB Security Plan being updated (Yes/No)?
Yes
e.Are Test Scripts/Cases being created/updated (Yes/No)? | Yes
f.Is a Requirements Traceability Matrix (RTM) being created/updated (Yes/No)? | Yes
4.Does the data inventory need to be updated (Yes/No)? | Yes, <placeholder>, id
5.Business QA Agreement to Develop (Only components requiring quality oversight) | Vivek Yadav
Deployment Plan
1.Is this change an emergency? If yes, record names of persons agreeing to implement (Technical Approver), method of agreement, date of agreement, and justification
2.Document implementation plan/actions, including required interactions (such as user training) with associated change requests, sites or business customers. Detail how the code is to be installed into the production environment including the deployment to production process | <placeholder Git repo>,<place holder operation team>
3.Parties involved in the deployment. | <placeholder>, <development team member>
4.Verify the metadata values in production against the values documented in the Data Inventory.Document the results of the verification in the related CTASK and document the CTASK completion date in the Development Execution Notes. | Yes,CTASK45090
5.Is this the deployment of new component (Yes/No) ? | Yes
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Good template!, lets address the comments I've added.
Note on A15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: So for requirements and other documentation, add other scenarios as well: 1) Existing Requirements might be updated. 2) No Change to existing requirement user story. Same goes for Design document.
Note on A24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test Scripts might be created, existing might be updated, regression of previous test scripts might be done. Provision your input/output string accordingly.
Note on A26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: RTM's are newly created in case there is a new component, and updated for changes to existing components. Add Link in case RTM is getting updated. If needed, I can show how RTM look like.
Note on C28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added the option for no.
Note on A30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added content since it was blank.
Note on C33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Emergency changes are extremely rare, no need to add.
Note on A34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: You'll find details for this in Deployment Plan under Deploy tab.
Note on C35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Minor change made
Note on C36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Minor change made.